## Sheet1
Menu Option | Description | Old Name | Ref | Resource | Status | Days Remaining | Essential?
Summary Workbench | Summary Workbench form | Summary Workbench | 4.5.2/4.5.6 | LE | Ongoing | 7 | Yes
Detailed Parameters | Update detailed workbench using parameter selection | Detailed Workbench | 4.5.1/4.5.5 | ML | Complete | 0 | Yes
Detailed Focus Groups | Update detailed workbench using focus group selection | Detailed Workbench | 4.5.1/4.5.5 | ML | Complete | 0 | Yes
Detailed workbench | Detailed workbench form | Detailed Workbench | 4.5.1/4.5.5 | ML | Ongoing | 2 | Yes
Stowaway Stores |  |  | 4.5.10 | ML | Not started | 2 | Yes
Manual APP Release |  | SRR Manual Allocation |  | ML | Complete | 0 | Yes
Stowaway APP Release |  |  | 4.5.12 | ML | Complete | 0 | Yes
User Dept Authority | Assign users to department | User dept authority maintenance |  | ML | Complete | 0 | Yes
Store Deletion Schedule |  |  | 4.5.4 | ML | Not started | 2 | No
Item/Store Assignment | Assign items to stores | Item/Detail entry |  | ML | In progress | 1 | No
Min Display Qty | Set min display quantity for items | Minimum Dsp Quantity Maintenance |  | ML | Complete | 0 | Yes
Store Lead Times | Set lead times for stores | Store Lead Time Maintenance |  | ML | Complete | 0 | Yes
Department Store Grades | Change dept/grade hierarchy for stores |  | 4.5.3 | ML | Complete | 0 | Yes
Workbench Extract | Start extract job on AS400 | Central Planning Workbench Extract |  | ML | Complete | 0 | Yes
User Interface Timeout |  |  | 4.5.11 | ML | Complete | 0 | Yes
System Available Polling |  |  |  | ML | Complete | 0 | Yes
System Message Polling |  |  |  | ML | Complete | 0 | Yes
Packaging & Deployment testing |  |  |  | ML | Not started | 1 | Yes
Local Data Mananger | Management of users, environments, menus and applications |  |  | TBA | Not started | 5 | No
Local Data Population | Populate LocalData.sdf from live XML files |  |  | TBA | Not started | 1 | Yes
|  |  | TOTALS |  |  | 21
|  |  | Essential for 1st day UAT |  |  | 13
|  |  | Extras, ok to be delivered during UAT |  |  | 8
Note on G2: LE to provide more accurate time to complete.